## Summary
The Table displays NSRS payments by funding source and fiscal year.
Fund Source
Fiscal Year | Washoe County CIP - PW920498 | WCRCS Infrastrcture - C210300 | Partner Agency Pre-Pay - C210330 | Bond (NSRS Debt 2020) - PW920408 | Total Payments | Notes
FY19 | 619191.74 |  |  |  | 619191.74 | MileStone Payment 1; Project Management
FY20 | 417989.99 | 750000 |  |  | 1167989.99 | MileStone Payment 2; Project Management; Change Order 1; Bond Consultant Fees; $134,421 Reibursement from 911 Fund for Consoles
FY21 | 212818.87 |  | 800000 | 671758.18 | 1684577.05 | NSC Completion Milestone (3); Project Management; Peavine Grounding; Civils Change Order #1; Microwave Change Order; Completion of field path surveys
FY22 |  |  |  | 4462278.86 | 4462278.86 | Completion of DDR R2 Milestone; Microwave payment 2-4; P25 Hardware Factory Staging; P25 Hardware shipment and delivery milestone; power connection fee for Cold Springs
FY23 |  |  |  | 2581038.76 | 2581038.76 | Civils Change Order 12; Microwave payment 5-7; Ophir Batteries; LCP-Tracker; CMAR RFP Ad
FY24 |  |  |  | 118150.67 | 118150.67 | Biltmore work with RX3
Totals | 1250000.6 | 750000 | 800000 | 7833226.47 | 10633227.07
Starting Balance |  |  | 3190941.54 | 10319130.99 | 13510072.53 | $10,319,130.99 was the total amount funded through bond financing.
Remaining Funds |  |  | 2390941.54 | 2485904.52 | 4876846.06 | $4,876,846 remains available for future milestone payments and construction.

## FY19 Expenses
Washoe County CIP - PW920498
Predecessor document number | Commitment item name | Funds Management - Update Date | Order | Cost Center | WBS Element | Commitment Item | Business Area | Amount to be checked against payment bud | Reference Document Number | Name | Reference | Text | Document Header Text | CO Transaction | Document Type
| Prof Services | 2019-02-20 |  |  | PW920498.8 | 710100 | 01 | 3485 | 119065391 |  | TECHSERVSD022019 | Correcting CC for Fed. Engineering Services NSRS | Correcting CC/GLs 108-0 | FI: Postings | JE
3485
6500002654 | Prof Services | 2018-12-27 |  |  | PW920498.8 |  | 01 | 9710 | 5119009059 | FEDERAL ENGINEERING INC | 2018-4-4556 |  | AX_INV_448110 | Incoming invoice | RE
6500002654 | Prof Services | 2018-12-27 |  |  | PW920498.8 |  | 01 | 733.89 | 5119009059 |  | 2018-4-4556 |  | AX_INV_448110 | Incoming invoice | RE
6500002654 | Prof Services | 2019-02-13 |  |  | PW920498.8 |  | 01 | 7712.5 | 5119011717 |  | 2019-1-4578 |  | AX_INV_456021 | Incoming invoice | RE
6500002654 | Prof Services | 2019-03-05 |  |  | PW920498.8 |  | 01 | 7462.5 | 5119012747 |  | 2019-1-4579 |  | AX_INV_459309 | Incoming invoice | RE
6500002654 | Prof Services | 2019-04-05 |  |  | PW920498.8 |  | 01 | 9300 | 5119014706 |  | 2019-2-4581 |  | AX_INV_463167 | Incoming invoice | RE
6500002654 | Prof Services | 2019-05-08 |  |  | PW920498.8 |  | 01 | 6760 | 5119016582 |  | 2019-2-4588 |  | AX_INV_466615 | Incoming invoice | RE
6500002654 | Prof Services | 2019-06-10 |  |  | PW920498.8 |  | 01 | 22597.5 | 5119018343 |  | 2019-2-4590 |  | AX_INV_471285 | Incoming invoice | RE
6500002654 | Prof Services | 2019-06-10 |  |  | PW920498.8 |  | 01 | 6141.1 | 5119018343 |  | 2019-2-4590 |  | AX_INV_471285 | Incoming invoice | RE
6500002654 | Prof Services | 2019-06-11 |  |  | PW920498.8 |  | 01 | 3691.5 | 5119018478 |  | 2019-2-9299 |  | AX_INV_471555 | Incoming invoice | RE
6500002654 | Prof Services | 2019-06-30 |  |  | PW920498.8 |  | 01 | 7616.5 | 5119019912 |  | 2019-3-4592 |  | AX_INV_474402 | Incoming invoice | RE
[8 empty] | 81725.49 |  | FEDERAL ENGINEERING INC
[6 empty] | 710100 |  | 85210.49
6500002623 | Comm Equip Capital | 2018-10-31 |  |  | PW920498.6 | 781010 | 01 | 533981.25 | 5119005962 | HARRIS CORP. PUBLIC SAFETY AND | WASHOE0001 |  | AX_INV_443449 | Incoming invoice | RE
[8 empty] | 533981.25 |  | HARRIS CORP. PUBLIC SAFETY AND
[6 empty] | 781010 |  | 533981.25
619191.74
Note on A2: Predecessor document number
Note on B2: Commitment item name
Note on C2: Funds Management - Update Date
Note on D2: Order
Note on E2: Cost Center
Note on F2: WBS Element
Note on G2: Commitment Item
Note on H2: Business Area
Note on I2: Amount to be checked against payment bud
Note on J2: Reference Document Number
Note on K2: Name
Note on L2: Reference
Note on M2: Text
Note on N2: Document Header Text
Note on O2: CO Transaction
Note on P2: Document Type

## FY20 Expenses
Washoe County CIP - PW920498
Predecessor document number | Commitment item name | Funds Management - Update Date | Order | Cost Center | WBS Element | Commitment Item | Business Area | Amount to be checked against payment bud | Reference Document Number | Name | Reference | Text | Document Header Text | CO Transaction | Document Type
| Prof Services | 2020-03-27 |  |  | PW920498.8 | 710100 | 01 | 16914.14 | 1920058387 | **DNU **PFM ASSET MANAGEMENT LLC | 108313 | *Invoice 108313 - Washoe County | AX_INV_508018 | FI: Postings | KR
| Prof Services | 2020-04-06 |  |  | PW920498.8 |  | 01 | 11375 | 1920058391 |  | 105615 | *Invoice 105615-Washoe County | AX_INV_508947 | FI: Postings | KR
[8 empty] | 28289.14 |  | **DNU **PFM ASSET MANAGEMENT LLC
6500002654 | Prof Services | 2019-08-26 |  |  | PW920498.8 |  | 01 | 6235 | 5120002442 | FEDERAL ENGINEERING INC | 2019-3-4593 |  | AX_INV_478000 | Incoming invoice | RE
6500002654 | Prof Services | 2019-09-11 |  |  | PW920498.8 |  | 01 | 9307 | 5120003559 |  | 2019-3-4594 |  | AX_INV_482727 | Incoming invoice | RE
6500002654 | Prof Services | 2019-09-11 |  |  | PW920498.8 |  | 01 | 1240.96 | 5120003559 |  | 2019-3-4594 |  | AX_INV_482727 | Incoming invoice | RE
6500002654 | Prof Services | 2019-10-15 |  |  | PW920498.8 |  | 01 | 6703.5 | 5120005606 |  | 2019-4-4595 |  | AX_INV_485890 | Incoming invoice | RE
6500002654 | Prof Services | 2019-10-15 |  |  | PW920498.8 |  | 01 | 632.68 | 5120005606 |  | 2019-4-4595 |  | AX_INV_485890 | Incoming invoice | RE
6500002654 | Prof Services | 2019-11-12 |  |  | PW920498.8 |  | 01 | 9452.5 | 5120007099 |  | 2019-4-4596 |  | AX_INV_491179 | Incoming invoice | RE
6500002654 | Prof Services | 2019-11-12 |  |  | PW920498.8 |  | 01 | 683.69 | 5120007099 |  | 2019-4-4596 |  | AX_INV_491179 | Incoming invoice | RE
6500002654 | Prof Services | 2019-12-05 |  |  | PW920498.8 |  | 01 | 14788.5 | 5120008546 |  | 2019-4-4597 |  | AX_INV_494169 | Incoming invoice | RE
6500002654 | Prof Services | 2019-12-05 |  |  | PW920498.8 |  | 01 | 2553.68 | 5120008546 |  | 2019-4-4597 |  | AX_INV_494169 | Incoming invoice | RE
6500002654 | Prof Services | 2020-01-06 |  |  | PW920498.8 |  | 01 | 4009 | 5120010314 |  | 2020-1-4598 |  | AX_INV_497904 | Incoming invoice | RE
6500002654 | Prof Services | 2020-02-06 |  |  | PW920498.8 |  | 01 | 17709.27 | 5120012079 |  | 2020-1-4599 |  | AX_INV_501814 | Incoming invoice | RE
6500002654 | Prof Services | 2020-02-06 |  |  | PW920498.8 |  | 01 | 2894.67 | 5120012079 |  | 2020-1-4599 |  | AX_INV_501814 | Incoming invoice | RE
6500002654 | Prof Services | 2020-03-03 |  |  | PW920498.8 |  | 01 | 8218 | 5120013398 |  | 2020-1-4600 |  | AX_INV_504951 | Incoming invoice | RE
6500002654 | Prof Services | 2020-03-03 |  |  | PW920498.8 |  | 01 | 648.4 | 5120013398 |  | 2020-1-4600 |  | AX_INV_504951 | Incoming invoice | RE
6500002654 | Prof Services | 2020-04-08 |  |  | PW920498.8 |  | 01 | 6173 | 5120015411 |  | 2020-2-4601 |  | AX_INV_508549 | Incoming invoice | RE
6500002654 | Prof Services | 2020-05-05 |  |  | PW920498.8 |  | 01 | 7928 | 5120017153 |  | 2020-2-4602 |  | AX_INV_512678 | Incoming invoice | RE
6500002654 | Prof Services | 2020-06-30 |  |  | PW920498.8 |  | 01 | 6563 | 5120020352 |  | 2020-2-4603 |  | AX_INV_516075 | Incoming invoice | RE
6500002654 | Prof Services | 2020-06-30 |  |  | PW920498.8 |  | 01 | 5141 | 5120020470 |  | 2020-3-4604 |  | AX_INV_519659 | Incoming invoice | RE
[8 empty] | 110881.85 |  | FEDERAL ENGINEERING INC
| Prof Services | 2020-03-26 |  |  | PW920498.8 |  | 01 | 3575 | 1920058151 | HOBBS ONG AND ASSOCIATES INC | WASHOE-2019-02 | *NV Shared Radio System-Washoe | AX_INV_507865 | FI: Postings | KR
[8 empty] | 3575 |  | HOBBS ONG AND ASSOCIATES INC
[6 empty] | 710100 |  | 142745.99
| Comm Equip Capital | 2019-12-17 |  |  | PW920498.6 | 781010 | 01 | -134421 | 120043978 |  | TECHSERVSD121719 | E911 Reimbsmt 3 Consoles apvl 1/17/19 PO45x40259-1 | E911 Reimbsble 3 Consoles | FI: Postings | JE
-134421
6500002623 | Comm Equip Capital | 2019-11-13 |  |  | PW920498.6 |  | 01 | 45304.43 | 5120007300 | HARRIS CORP. PUBLIC SAFETY AND | WASHOECO092319_C |  | AX_INV_491748 | Incoming invoice | RE
4500040259 | Comm Equip Capital | 2019-12-12 |  |  | PW920498.6 |  | 01 | 134421 | 5020000274 |  |  |  |  | Goods receipt for purch. order | WE
6500002623 | Comm Equip Capital | 2019-12-23 |  |  | PW920498.6 |  | 01 | 796005.24 | 5120009706 |  | 1122201901 CM |  | AX_INV_496640 | Incoming invoice | RE
6500002623 | Comm Equip Capital | 2020-02-27 |  |  | PW920498.6 |  | 01 | 183934.33 | 5120013117 |  | WASHOE012720CM |  | AX_INV_504298 | Incoming invoice | RE
[8 empty] | 1159665 |  | HARRIS CORP. PUBLIC SAFETY AND
[6 empty] | 781010 |  | 1025244
1167989.99
Note on A2: Predecessor document number
Note on B2: Commitment item name
Note on C2: Funds Management - Update Date
Note on D2: Order
Note on E2: Cost Center
Note on F2: WBS Element
Note on G2: Commitment Item
Note on H2: Business Area
Note on I2: Amount to be checked against payment bud
Note on J2: Reference Document Number
Note on K2: Name
Note on L2: Reference
Note on M2: Text
Note on N2: Document Header Text
Note on O2: CO Transaction
Note on P2: Document Type

## FY21 Expenses
Bond (NSRS Debt 2020) - PW920408
Predecessor document number | Commitment item name | Funds Management - Update Date | Order | Cost Center | WBS Element | Commitment Item | Business Area | Amount to be checked against payment bud | Reference Document Number | Name | Reference | Text | Document Header Text | CO Transaction | Document Type
| Prof Services | 2020-10-12 |  |  | PW920408.8 | 710100 | 01 | 19553.5 | 121017576 |  | TECHSERVSD101220 | Fed. Eng. 65x2654 move from 920498.8 to 920408.8 | NSRS Fed Eng Prof'l Svcs | FI: Postings | JE
| Prof Services | 2021-05-20 |  |  | PW920408.8 |  | 01 | -58201.75 | 121058323 |  | TECHSERVSD052021 | FY21 FederalEng PO#65x2654 s/b 210010 not 920408 | FY21 FedEng Radio System | FI: Postings | JE
-38648.25
6500002654 | Prof Services | 2020-11-03 |  |  | PW920408.8 |  | 01 | 9508.25 | 5121005412 | FEDERAL ENGINEERING INC | 2020-4-4608 |  | AX_INV_534622 | Incoming invoice | RE
6500002654 | Prof Services | 2020-12-02 |  |  | PW920408.8 |  | 01 | 5298 | 5121006638 |  | 2020-4-4609 |  | AX_INV_537668 | Incoming invoice | RE
6500002654 | Prof Services | 2021-01-13 |  |  | PW920408.8 |  | 01 | 2454 | 5121008651 |  | 2021-1-4610 |  | AX_INV_541498 | Incoming invoice | RE
6500002654 | Prof Services | 2021-02-02 |  |  | PW920408.8 |  | 01 | 5552.5 | 5121009577 |  | 2021-1-4611 |  | AX_INV_544856 | Incoming invoice | RE
6500002654 | Prof Services | 2021-03-03 |  |  | PW920408.8 |  | 01 | 6526.25 | 5121010909 |  | 2021-1-4612 |  | AX_INV_548248 | Incoming invoice | RE
6500002654 | Prof Services | 2021-04-05 |  |  | PW920408.8 |  | 01 | 14620 | 5121012505 |  | 2021-2-4613 |  | AX_INV_551706 | Incoming invoice | RE
6500002654 | Prof Services | 2021-05-04 |  |  | PW920408.8 |  | 01 | 14242.75 | 5121014148 |  | 2021-2-4614 |  | AX_INV_555977 | Incoming invoice | RE
6500002654 | Prof Services | 2021-06-09 |  |  | PW920408.8 |  | 01 | 7928 | 5121016031 |  | 2021-2-4615 |  | AX_INV_559727 | Incoming invoice | RE
6500002654 | Prof Services | 2021-06-30 |  |  | PW920408.8 |  | 01 | 6527.5 | 5121017329 |  | 2021-3-4616 |  | AX_INV_563582 | Incoming invoice | RE
[8 empty] | 72657.25 |  | FEDERAL ENGINEERING INC
6500003415 | Prof Services | 2020-11-12 |  |  | PW920408.6 |  | 01 | 26980 | 5121005792 | RADCO COMMUNICATIONS LLC | 20298 |  | AX_INV_535645 | Incoming invoice | RE
[8 empty] | 26980 |  | RADCO COMMUNICATIONS LLC
[6 empty] | 710100 |  | 60989
6500002623 | Construction Contrac | 2020-09-11 |  |  | PW920408.6 | 781080 | 01 | 797255.26 | 5121002895 | HARRIS CORP. PUBLIC SAFETY AND | WASHOE0707202002 |  | AX_INV_528660 | Incoming invoice | RE
6500002623 | Construction Contrac | 2020-09-29 |  |  | PW920408.6 |  | 01 | 322048 | 5121003582 |  | WASHOE070720201C |  | AX_INV_530413 | Incoming invoice | RE
6500002623 | Construction Contrac | 2020-10-28 |  |  | PW920408.6 |  | 01 | 116586.37 | 5121005062 |  | WSH0928202001CM |  | AX_INV_533881 | Incoming invoice | RE
6500002623 | Construction Contrac | 2021-04-26 |  |  | PW920408.6 |  | 01 | 174879.55 | 5121013721 |  | WASHOE0315202101 |  | AX_INV_555185 | Incoming invoice | RE
[8 empty] | 1410769.18 |  | HARRIS CORP. PUBLIC SAFETY AND
[6 empty] | 781080 |  | 1410769.18
1471758.18
Washoe County CIP - PW920498
Predecessor document number | Commitment item name | Funds Management - Update Date | Order | Cost Center | WBS Element | Commitment Item | Business Area | Amount to be checked against payment bud | Reference Document Number | Name | Reference | Text | Document Header Text | CO Transaction | Document Type
6500002623 | Construction Contrac | 2020-09-11 |  |  | PW920498.6 | 781080 | 01 | 212818.27 | 5121002895 | HARRIS CORP. PUBLIC SAFETY AND | WASHOE0707202002 |  | AX_INV_528660 | Incoming invoice | RE
[8 empty] | 212818.27 |  | HARRIS CORP. PUBLIC SAFETY AND
[6 empty] | 781080 |  | 212818.27
212818.27
[7 empty] | Total | 1684576.45
Note on A2: Predecessor document number
Note on B2: Commitment item name
Note on C2: Funds Management - Update Date
Note on D2: Order
Note on E2: Cost Center
Note on F2: WBS Element
Note on G2: Commitment Item
Note on H2: Business Area
Note on I2: Amount to be checked against payment bud
Note on J2: Reference Document Number
Note on K2: Name
Note on L2: Reference
Note on M2: Text
Note on N2: Document Header Text
Note on O2: CO Transaction
Note on P2: Document Type
Note on A29: Predecessor document number
Note on B29: Commitment item name
Note on C29: Funds Management - Update Date
Note on D29: Order
Note on E29: Cost Center
Note on F29: WBS Element
Note on G29: Commitment Item
Note on H29: Business Area
Note on I29: Amount to be checked against payment bud
Note on J29: Reference Document Number
Note on K29: Name
Note on L29: Reference
Note on M29: Text
Note on N29: Document Header Text
Note on O29: CO Transaction
Note on P29: Document Type

## FY22 Expenses
Bond (NSRS Debt 2020) - PW920408 | [15 empty] | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408 | Bond (NSRS Debt 2020) - PW920408
Predecessor document number | Commitment item name | Funds Management - Update Date | Order | Cost Center | WBS Element | Commitment Item | Business Area | Amount to be checked against payment bud | Reference Document Number | Name | Reference | Text | Document Header Text | CO Transaction | Document Type
6500002623 | Construction Contrac | 2021-12-16 |  |  | PW920408.6 | 781080 | 01 | 918728.31 | 5122008107 | HARRIS CORP. PUBLIC SAFETY AND | WASHOE1122202101 |  | AX_INV_582705 | Incoming invoice | RE
6500002623 | Construction Contrac | 2021-12-16 |  |  | PW920408.6 |  | 01 | 349759.1 | 5122008108 |  | WASHOE1122202103 |  | AX_INV_582713 | Incoming invoice | RE
6500002623 | Construction Contrac | 2021-12-16 |  |  | PW920408.6 |  | 01 | 116586.37 | 5122008109 |  | WASHOE1122202102 |  | AX_INV_582714 | Incoming invoice | RE
6500002623 | Construction Contrac | 2022-03-03 |  |  | PW920408.6 |  | 01 | 1592010.48 | 5122011968 |  | WASHOE0211202202 |  | AX_INV_592745 | Incoming invoice | RE
6500002623 | Construction Contrac | 2022-03-03 |  |  | PW920408.6 |  | 01 | 1194007.86 | 5122011970 |  | WASHOE0211202201 |  | AX_INV_592749 | Incoming invoice | RE
6500002623 | Construction Contrac | 2022-03-30 |  |  | PW920408.6 |  | 01 | 233172.74 | 5122013550 |  | WASHOE0211202203 |  | AX_INV_592750 | Incoming invoice | RE
[8 empty] | 4404264.86 |  | HARRIS CORP. PUBLIC SAFETY AND
6500004170 | Construction Contrac | 2022-05-19 |  |  | PW920408.6 |  | 01 | 58014 | 5122016398 | NV ENERGY | 3007416177 |  | AX_INV_605512 | Incoming invoice | RE
[8 empty] | 58014 |  | NV ENERGY
[6 empty] | 781080 |  | 4462278.86
4462278.86
Note on A2: Predecessor document number
Note on B2: Commitment item name
Note on C2: Funds Management - Update Date
Note on D2: Order
Note on E2: Cost Center
Note on F2: WBS Element
Note on G2: Commitment Item
Note on H2: Business Area
Note on I2: Amount to be checked against payment bud
Note on J2: Reference Document Number
Note on K2: Name
Note on L2: Reference
Note on M2: Text
Note on N2: Document Header Text
Note on O2: CO Transaction
Note on P2: Document Type

## FY23 Expenses
Bond (NSRS Debt 2020) - PW920408
Predecessor document number | Commitment item name | Funds Management - Update Date | Order | Cost Center | WBS Element | Commitment Item | Business Area | Amount to be checked against payment bud | Reference Document Number | Name | Reference | Text | Document Header Text | CO Transaction | Document Type
6500004615 | Software Subscriptio | 2022-12-16 |  |  | PW920408.8 | 710212 | 01 | 6543.4 | 5123008146 | LCPTRACKER INC | IR-21033 |  | AX_INV_629649 | Incoming invoice | RE
[8 empty] | 6543.4 |  | LCPTRACKER INC
[6 empty] | 710212 |  | 6543.4
| Advertising | 2023-05-09 |  |  | PW920408.6 | 710546 | 01 | 191 | 1923089728 | DNU - RENO NEWSPAPERS INC | 0005678036 |  | AX_INV_654820 | FI: Postings | KR
[8 empty] | 191 |  | DNU - RENO NEWSPAPERS INC
[6 empty] | 710546 |  | 191
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 | 781004 | 01 | 13500 | 5023000181 | NOR-CAL BATTERY CO |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 37125 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 645 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 1695 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 7875 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 17352 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 123 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 4593 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | 3000 | 5023000181 |  |  |  |  | Goods receipt for purch. order | WE
4500041556 | Equipment Capital | 2022-10-25 |  |  | PW920408.6 |  | 01 | -1022.91 | 5123005399 |  | P246420 |  | AX_INV_625420 | Incoming invoice | RE
[8 empty] | 84885.09 |  | NOR-CAL BATTERY CO
[6 empty] | 781004 |  | 84885.09
6500002623 | Construction Contrac | 2022-09-29 |  |  | PW920408.6 | 781080 | 01 | 116586.37 | 5123003892 | HARRIS CORP. PUBLIC SAFETY AND | WASHOE0923202201 |  | AX_INV_623287 | Incoming invoice | RE
6500002623 | Construction Contrac | 2022-09-29 |  |  | PW920408.6 |  | 01 | 116586.37 | 5123003893 |  | WASHOE0923202202 |  | AX_INV_623288 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 13262.1 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 398127.83 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 184793.75 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 676649.55 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 9420.1 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 292498.43 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 385061.57 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 291472.2 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
6500002623 | Construction Contrac | 2023-03-03 |  |  | PW920408.6 |  | 01 | 4961 | 5123012284 |  | WASHOE0228202302 |  | AX_INV_644272 | Incoming invoice | RE
[8 empty] | 2489419.27 |  | HARRIS CORP. PUBLIC SAFETY AND
[6 empty] | 781080 |  | 2489419.27
2581038.76
Note on A2: Predecessor document number
Note on B2: Commitment item name
Note on C2: Funds Management - Update Date
Note on D2: Order
Note on E2: Cost Center
Note on F2: WBS Element
Note on G2: Commitment Item
Note on H2: Business Area
Note on I2: Amount to be checked against payment bud
Note on J2: Reference Document Number
Note on K2: Name
Note on L2: Reference
Note on M2: Text
Note on N2: Document Header Text
Note on O2: CO Transaction
Note on P2: Document Type

## FY24 Expenses
Bond (NSRS Debt 2020) - PW920408
Predecessor document number | Commitment item name | Funds Management - Update Date | Order | Cost Center | WBS Element | Commitment Item | Business Area | Amount to be checked against payment bud | Reference Document Number | Name | Reference | Text | Document Header Text | CO Transaction | Document Type
6500005271 | Prof Services | 2023-09-26 |  |  | PW920408.8 | 710100 | 01 | 22940 | 5124003942 | RX3 COMMUNICATIONS, INC. | 16555 |  | AX_INV_672235 | Incoming invoice | RE
6500005271 | Prof Services | 2023-09-26 |  |  | PW920408.8 |  | 01 | 5796 | 5124003942 |  | 16555 |  | AX_INV_672235 | Incoming invoice | RE
6500005271 | Prof Services | 2023-09-26 |  |  | PW920408.8 |  | 01 | 3900 | 5124003942 |  | 16555 |  | AX_INV_672235 | Incoming invoice | RE
6500005324 | Prof Services | 2023-11-06 |  |  | PW920408.8 |  | 01 | 17648 | 5124006132 |  | 16815 |  | AX_INV_677330 | Incoming invoice | RE
6500005324 | Prof Services | 2023-11-06 |  |  | PW920408.8 |  | 01 | 5000 | 5124006132 |  | 16815 |  | AX_INV_677330 | Incoming invoice | RE
6500005324 | Prof Services | 2023-11-06 |  |  | PW920408.8 |  | 01 | 3900 | 5124006132 |  | 16815 |  | AX_INV_677330 | Incoming invoice | RE
6500005271 | Prof Services | 2023-12-13 |  |  | PW920408.8 |  | 01 | 12480 | 5124008219 |  | 16960 |  | AX_INV_683102 | Incoming invoice | RE
6500005324 | Prof Services | 2023-12-14 |  |  | PW920408.8 |  | 01 | 7500 | 5124008361 |  | 16961 |  | AX_INV_683101 | Incoming invoice | RE
6500005324 | Prof Services | 2023-12-14 |  |  | PW920408.8 |  | 01 | 15015 | 5124008361 |  | 16961 |  | AX_INV_683101 | Incoming invoice | RE
6500005324 | Prof Services | 2024-01-05 |  |  | PW920408.8 |  | 01 | 7500 | 5124009459 |  | 17092 |  | AX_INV_687350 | Incoming invoice | RE
6500005324 | Prof Services | 2024-01-05 |  |  | PW920408.8 |  | 01 | 15015 | 5124009459 |  | 17092 |  | AX_INV_687350 | Incoming invoice | RE
[8 empty] | 116694 |  | RX3 COMMUNICATIONS, INC.
[6 empty] | 710100 |  | 116694
| Software Subscriptio | 2023-07-26 |  |  | PW920408.8 | 710212 | 01 | 1456.67 | 1924002767 | LCPTRACKER INC | IR-23451 | LCP TRACKER PROJECT CAPACITY INCREASE | AX_INV_663077 | FI: Postings | KR
[8 empty] | 1456.67 |  | LCPTRACKER INC
[6 empty] | 710212 |  | 1456.67
118150.67
Note on A2: Predecessor document number
Note on B2: Commitment item name
Note on C2: Funds Management - Update Date
Note on D2: Order
Note on E2: Cost Center
Note on F2: WBS Element
Note on G2: Commitment Item
Note on H2: Business Area
Note on I2: Amount to be checked against payment bud
Note on J2: Reference Document Number
Note on K2: Name
Note on L2: Reference
Note on M2: Text
Note on N2: Document Header Text
Note on O2: CO Transaction
Note on P2: Document Type