## Link-by-link
Site Name | Edison Way | Ophir Peak | Peavine Mtn | Red Peak | Slide Mtn | Sparks Dispatch | Spectrum | Spare Equipment | Grand Total
v4 Radio Equipment | 20878.065 | 33402.645 | 48739.325 | 32602.945 | 45161.865 | 20878.065 | 40675.245 | 40939.4 | 283277.555
v4 Antennas | 5177.642 | 15477.014 | 37693.642 | 20264.52 | 26661.058 | 5519.662 | 19910.702 | 0 | 130704.24
Addt'l Mtrl Discount | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -28000
Material Sale Price | 28194.6337 | 56724.5737 | 103666.2087 | 61709.3312 | 85403.6537 | 28622.1587 | 71357.4337 | 46799.25 | 482477.2437
v4 Engineering Svc | 6683.15 | 6683.15 | 6683.15 | 6683.15 | 6683.15 | 6683.15 | 6683.15 |  | 46782.05
v4 Installation Svc | 25369.4181 | 29313.1605 | 55376.2155 | 37465.62 | 43416.7263 | 25525.764 | 45390.6794 | 15120.215 | 276977.799
v4 Addt'l Services | 4137.5 | 4137.5 | 4137.5 | 4137.5 | 4137.5 | 4137.5 | 4137.5 | 0 | 28962.5
Services Sale Price | 47770.8899 | 52976.6299 | 87379.8625 | 63737.8764 | 71593.3368 | 47977.2665 | 74198.9549 | 19958.6838 | 465593.5007
Total | 75965.5237 | 109701.2037 | 191046.0712 | 125447.2077 | 156996.9905 | 76599.4253 | 145556.3886 | 66757.9338 | 948070.7445
Microwave Design Change Order
Site Name | Edison Way | Ophir Peak | Peavine Mtn | Red Peak | Slide Mtn | Sparks Dispatch | Spectrum | Spare Microwave Equipment | Grand Total
v7 Radio Equipment | 21395.565 | 33920.145 | 49054.325 | 33123.505 | 45679.365 | 21395.565 | 41192.745 | 48484.4 | 294245.615
v7 Antennas | 3871.638 | 17674.9628 | 39629.6118 | 22356.821 | 24119.994 | 4167.682 | 20565.0488 | 28398.2075 | 160783.9659
Addt'l Mtrl Discount | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -28000
Material Sale Price | 27209.0037 | 60118.8847 | 106479.921 | 64975.4075 | 82874.1987 | 27579.0588 | 72822.2422 | 91728.2594 | 533786.9761
Material Variance | -985.63 | 3394.311 | 2813.7123 | 3266.0763 | -2529.455 | -1043.1 | 1464.8085 | 44929.0094 | 51309.7324
v7 Engineering & PM Svc | 7520 | 18461.95 | 7520 | 7520 | 7520 | 7520 | 7520 | 0 | 63581.95
v7 Installation Svc | 39630.25 | 39630.25 | 78019.35 | 30000 | 39630.25 | 27594.82 | 39630.25 |  | 294135.17
Services Sale Price | 62238.33 | 76681.704 | 112911.942 | 49526.4 | 62238.33 | 46351.5624 | 62238.33 | 0 | 472186.5984
Services Variance | 14467.4401 | 23705.0741 | 25532.0795 | -14211.4764 | -9355.0068 | -1625.7041 | -11960.6249 | -19958.6838 | 6593.0977
Total | 89447.3337 | 136800.5887 | 219391.863 | 114501.8075 | 145112.5287 | 73930.6212 | 135060.5722 | 91728.2594 | 1005973.5745
| 1 microwave link | 1 out of 2 microwave links | 2 out of 6 microwave links | 1 out of 3 microwave links | 1 out of 4 microwave links | 1 microwave link | 7 Microwave Links |  | Total Costs by Microwave Link
911 Reimbursement | 89447.3337 | 68400.2944 | 73130.621 | 38167.2692 | 36278.1322 | 73930.6212 | 135060.5722 | 91728.2594 | 606143.1033
Note on I15: Taylor, Heather (US): Includes addt'l spare PAD-6 dish
Note on C20: Taylor, Heather (US): Additional site walk, license change

## Nokia Change Req - Orig (hidden)
CHANGE ORDERS: | Analysis | Cost | Value of Work Performed
Wednesday 8-17-2022 delivered Incline rack while waiting to do Edison Spectrum cut and gaining access to Ophir. | The 7/21/2022 MPP schedule I inherited from Kathy sent to L3H on 7/22/2022, shows Ophir to Spectrum from 8/17-8/24. The deployment schedule sent the same date shows 8/15-8/18/2022. I do not believe Nokia received any other schedule from L3 until 8/24/22 @ 5:01 PM wherein Heather sent 3 files and said "use this one." | 2813
9-6-2022 REMOB | 8/25-9/6/2022 - no activity. Came back to start Slide <> Rose | 19600
9-12-2022 REMOB | Wed 9/7/2022 - complete with Slide to Rose. No activity until Monday 9/12/2022 for Incline <> Snowflake | 19600
10-3-2022 REMOB LLD pull cards – pre-program updated LLD | Not billable - customer good will, even though this was a customer request | 0 | 14745
10-4-2022 EDISON AIR SYSTEM VERIFIED WORKING CORRECTLY | Crews started at Edison and troubleshot the reported low / no pressurization. Crew found the new waveguide and airline was holding pressure and could not locate an issue with their work. No trouble found (NTF). The crew did adjust the existing dehydrator output to increase it to 3 psi | 14745
10-5-2022 -OPHIR TROUBLESHOOT AIR LEAK | Not billable - Nokia "warranty" | 0
10-6-2022 – OPHIR - REPLACE WG | Not billable | 0
10-10-2022 - REMOB Incline to Snowflake | As of end of day 9/7/2022 when Alan left for vacation, the Incline to Snowflake hop was scheduled for Tuesday 9/12 and cut 9/13. During my absence this pushed to Monday 10/10/2022 | 19600
10-11-2022 – CREW DOWN HOLD IN MARKET | While Nokia understands the need for scheduling outages in a live 911 network, the restrictions on days we could cut and notification timelines were not communicated at the inception of the project or included in the SOW. Nokia came to market with the intention of getting this cut done on the single day we were afforded to do it (Wednesday) and did not wish to delay the cut should one thing go wrong or take longer than expected. | 17545
10-24-2022 REMOB | Delayed from 10/13 to 10/24 for two reasons: | 9800
1) Nokia did not follow routing guide we had
2) Nokia did not have the current routing guide and the number it told us to call for FTL lost 2-3 days of time
This should be split 50/50
10-26-2022 Virginia < Peavine dish move from stub to large tower | Trip back to warehouse to locate longer WG. Path survey was done from the existing location on the stub tower and no change was communicated. The supplied floor plan does not show the dish location. | 5445
These notes are from the path survey review: Requires deinstallation of existing dish and line. Dish to Peavine existing 6' at 24' mounted on building structure.
The supplied floor plan does show Nokia using entry port 1 on the end of the building nearest the large tower, but this change was not called out.
10-26-2022 Virginia < Peavine ice shield requested were not in scope | L3H (Larry) requested that an ice shield be placed above the Virginia < Peavine dish and later moved to be above Virginia to Red Peak. Ice shield is not in scope here and neither is the future move. This is documented in the 10/26/2022 call notes | 3228.6
10-26-2022 WG for Fox < Peavine | Email from Randy: | 2346.12
The WG E60 150ft was picked up from the whse to install at Virginia Peak due to the dish location change from the current rooftop tower to the main tower.
The 146ft poito roll was buried at the back of the warehouse per washoe county, the 150ft was readily available.
The 146ft for Poito will be used to backfill the 150ft taken, leaving a need to re-order poito 146ft
54 vs 146 @ $10.33 / ft installed + $9.56 for materials
10-30 2022 – REMOVE DISHES FROM VIRGINIA AND FOX |  | 0 | 21777.78
10-31 2022 – REMOVE DISHES FROM VIRGINIA AND FOX |  | 0 | 21777.78
2-28-2023 - refile licenses |  | 4411
3/7/2023 - new system map + 2 TSE hours | Discovered in closeout of Edison that several site names changed, and some sites were dropped and added. L3H asked for updated map. | 600
3/10/2023 - reorder waveguide for Virginia Peak | For the path from Virginia Peak facing Peavine where we surveyed it mounted on top of the shelter but L3H/County wanted the antenna to be placed on the tower so longer waveguide was required. This change was never clearly called out and at best buried in a floorplan. 146' needs to be ordered. | 1395.76
121129.48